30-Day Onboarding Plan

Data Engineer / Data Analyst

Prepared for Shalmali

Start date: Monday, 17 August 2026

(Note: 15 Aug falls on a Saturday — this plan begins on the first working day, 17 Aug)

Prepared by Anna Feller · Headfound

# Welcome, Shalmali!

We're excited to have you join Hforce as our new Data Engineer / Data Analyst. This plan is designed to get you grounded in three things, in this order: what we build and why (the product), how we work as a team (our culture, values, and rituals), and finally the tools and processes you'll use day to day (Databricks, our data pipelines, and documentation).

You don't need to memorize everything below — treat it as a map. We'll check in regularly (see the cadence at the end) to adjust the pace to what's useful for you.

## How this plan is organized

- Week 1 — Product, People & How We Work: understand what Headfound does, meet the team, and learn our working rhythms and values.

- Week 2 — Data Landscape & Tooling: go deep on our data stack, pipelines, Databricks environment, and documentation.

- Week 3 — Hands-On Contribution: take on your first real (small) task with support.

- Week 4 — Ramp to Ownership: own a small piece of work end-to-end and set goals for the next 60/90 days.

# Before Day 1 — Pre-boarding Checklist

Anna / IT / HR to complete ahead of 17 August:

- Laptop and hardware ready and shipped/waiting at desk

- Accounts provisioned: email, Slack/Teams, Hforce, calendar, Databricks workspace, Git/repo access, data warehouse access (with least-privilege role to start)

- Calendar invites sent for all Week 1 meetings listed below

- Buddy assigned: Kamil (data analyst) — closest day-to-day point of contact in Week 1

- Data engineering process documentation shared in advance (already done ✔)

- Welcome message sent to the team introducing Shalmali and her start date

- Desk / seating arranged (if applicable)

# Week 1 — Product, People & How We Work

Goal: understand what we build, why it matters, and how the team operates day to day.

| Day | Focus | Activities | Owner |
| --- | --- | --- | --- |
| Mon 17 Aug | Welcome & Foundational Intros | - Intro General (Hforce): time tracking, leave policy, and core values walkthrough - Intro Product with Anna: what Headfound & Hforce do — AI-driven candidate search paired with personal recruitment consulting; four-dimensional matching (skills, culture, motivation, values); the product from a client's perspective - Intro Data Analytics with Kamil: first look at how the analytics side of the team works | HR / Anna / Kamil |
| Tue 18 Aug | Data Stack Deep-Dive | - Intro Databricks, led by the Hforce Data Science team: workspace layout, clusters, notebooks, access verification - Data Planning session: how sprint/task planning works for the data team - Data Analytics (session 2) with Kamil: key datasets, dashboards, deeper walkthrough - Intro Data Engineering with Szymon: pipelines, process documentation walkthrough, note on candidate PII / GDPR handling | Hforce Data Science Team / Kamil / Szymon |
| Wed 19 Aug | Start Working + Q&A | - Shalmali can start working — picks up a first small, well-scoped task - Q&A with Anna: address anything open from Monday/Tuesday's intros, clarify priorities | Shalmali / Anna |
| Thu 20 Aug | Embedded in the Team | - Join team rituals: stand-ups, Kanban/planning cadence, Linear etiquette - Continue first task, with Kamil/Szymon on standby for questions - Core values in practice; meet any remaining cross-functional stakeholders (sales/client success, engineering, leadership) | Shalmali / Team |
| Fri 21 Aug | Week 1 Wrap-up | - Continue / wrap up first task - Self-guided read-through of data engineering process documentation; list open questions - Week 1 retro with Anna: what's clear, what's fuzzy, adjust Week 2 plan if needed | Shalmali / Anna |

# Week 2 — Data Landscape & Tooling

Goal: go deep on the data stack — Databricks, pipelines, quality, and governance.

| Day | Focus | Activities | Owner |
| --- | --- | --- | --- |
| Mon 24 Aug | Data Architecture | - Guided tour of the overall data architecture: sources → pipelines → warehouse → dashboards - Identify where candidate, client, and matching-algorithm data live - Review data engineering docs together with Szymon — clarify anything unclear from Week 1 | Szymon |
| Tue 25 Aug | Pipelines in Practice | - Shadow Kamil or Szymon on a real pipeline run or dashboard refresh - Walk through how a new data source gets onboarded (schema, validation, deployment) - Environment setup: local dev tools, repo access, coding standards / style guide | Kamil / Szymon |
| Wed 26 Aug | Data Quality & Governance | - Data quality checks and monitoring: what's automated, what's manual - GDPR / candidate data handling: retention rules, access controls, anonymization practices - Meet the team member(s) responsible for data governance, if separate | Szymon |
| Thu 27 Aug | Cross-Functional Context | - Sit in on a client success or sales sync to see how data/dashboards get used downstream - Understand what metrics matter most to clients (placement speed, match quality) - Continue reviewing the backlog / ticket queue with Anna | Anna |
| Fri 28 Aug | Second Task / Expanding Ownership | - Take on a slightly larger second task, or expand the scope of the first one - Pair on scoping so expectations are clear - Week 2 retro with Anna | Anna |

# Week 3 — Hands-On Contribution

Goal: apply what she's learned on a real, small, well-scoped task.

| Day | Focus | Activities | Owner |
| --- | --- | --- | --- |
| Week 3 31 Aug – 4 Sep | Hands-On Contribution | - Work on the first assigned task with regular check-ins (daily async, or short syncs as needed) - Join daily stand-ups and the sprint planning / backlog grooming session as a full participant - Pairing session(s) with data engineer or analyst on anything unfamiliar (SQL patterns, notebook conventions, deployment process) - Continue building fluency in the codebase, docs, and dashboards used by the team - Mid-onboarding check-in with Anna around Day 15: feedback both ways, adjust pace | Shalmali / Team |

# Week 4 — Ramp to Ownership

Goal: take ownership of a small piece of work end-to-end and set goals beyond Day 30.

| Day | Focus | Activities | Owner |
| --- | --- | --- | --- |
| Week 4 7 – 11 Sep | Ramp to Ownership | - Take ownership of a slightly larger task or a small project end-to-end (with support on standby, not in the driver's seat) - Present what she's built/learned so far to the team (short, informal demo) - Identify 1–2 areas of the data stack to specialize in over the next quarter - Gather feedback from data engineer/analyst and any stakeholders she's worked with - 30-day review with Anna: recap, feedback both ways, set goals for Day 60 and Day 90 | Shalmali / Anna |

# 30 / 60 / 90-Day Goals

| Milestone | Goal | How we'll know |
| --- | --- | --- |
| Day 30 | Comfortable navigating the data stack, product, and team rituals; has shipped a first small task | First task completed and reviewed; can explain the data architecture unprompted |
| Day 60 | Owns a defined area of the data pipeline or a recurring analysis; contributes in planning | Independently handles tickets in her area; proactively flags data quality issues |
| Day 90 | Fully ramped: proposes improvements, mentors on her area of expertise, works with minimal oversight | Drives at least one improvement project from idea to delivery |

# Ongoing Support

## Cadence

- Daily: short async or in-person check-in during Weeks 1–2 (5–10 minutes)

- Weekly 1:1 with Anna throughout the 30 days, continuing afterward on a regular rhythm

- Buddy (Kamil, data analyst): open door for “no question is too small” Databricks/data questions

- Milestone check-ins: end of Week 1, Week 2, Day 15, and Day 30

## Anna's commitments as manager

- Protect the first two weeks from unrelated urgent asks so Shalmali can focus on ramping up

- Make sure feedback flows both ways — this plan should flex based on what's actually useful

- Be explicit about priorities and how her work connects to client outcomes

- Celebrate early wins publicly with the team

## Resources at a glance

- Hforce — time tracking, leave, core values

- Databricks workspace — primary environment for data work

- Data engineering process documentation — shared prior to start

- Team wiki / repo — coding standards, architecture docs